## Aktivitas
Nama
Tanggal | Aktivitas | Plan (Jumlah) | Executed (Jumlah) | Sisa (Jumlah) | Status (Tercapai, Tdk Tercapai) | Keterangan
2023-03-16 | Scripting SuperApps Rebranding | 13 | 7 | 6 | Tidak Tercapai | Ewallet: 1. Ovo Positive 2. Dana Positive 3. ShopeePay Positive 4. LinkAja Positive 5. LinkAja Syariah Positive 6. Gopay Positive Berbagi: 1. Dompet Dhuafa Positive + Negative 2. Rumah Zakat Indonesia Positive + Negative 3. Kitabisa Positive + Negative 4. Jadiberkah Positive + Negative Profile: 1. Change Profile Pic 2. Delete Profile Pic 3. Change Email Positive + Negative
2023-03-17 | Scripting SuperApps Rebranding | 13 | 13 | 0 | Tercapai | Paket Data: 1. Telkomsel Positive + Negative 2. XL Positive + Negative 3. Tri Positive + Negative 4. Indosat Positive + Negative Download Mutasi N/A e statement: 1. Download Mutasi N/A e statement Current transaction: 1. View list recent transaction ( history) N/A transfer Positive + Negative 2. Update list recent transaction (history) N/A transfer Positive + Negative
2023-03-20 | Running dan Fixing Script | 5 | 5 | 0 | Tercapai | Pulsa dan Paket Data: 1. Pulsa XL Positive 2. Paket Data XL Positive Berbagi via Virtual Accout: 3. Dompet Dhuafa Positive 4. Rumah Zakat Indonesia Positive 5. Pengecekan Mutasi dan Jurnal melalui T24
2023-03-21 | Running dan Fixing Script | 9 | 9 | 0 | Tercapai | 1. Update List Recent Transaction Positive + Negative 2. View List Recent Transaction Positive + Negative 3. Social Media 4. Paket Data Telkomsel Positive 5. Pulsa Telkomsel Positive 6. ShopeePay Positive 7. Paket Data XL Positive 8. Rumah Zakat Indonesia Positive 9. Dompet Dhuafa Positive
2023-03-24 | Running dan Fixing Script | 6 | 6 | 0 | Tercapai | 1. Pulsa Indosat 2. Paket Data Indosat 3. Pulsa Tri 4. Paket Data Tri 5. Pulsa Smartfren 6. Download Mutasi E-Statement
2023-03-27 | Running | 6 | 6 | 0 | Tercapai | 1. Pulsa Indosat Negative 2. Pulsa Tri Positive + Negative 3. Pulsa Smartfren Positive + Negative 4. Download Mutasi E-Statement 5. Dompet Dhuafa Negative 6. Rumah Zakat Indonesia Negative