## Aktivitas
Nama
Tanggal | Aktivitas | Plan (Jumlah) | Executed (Jumlah) | Sisa (Jumlah) | Status (Tercapai, Tdk Tercapai) | Keterangan
2023-03-16 | Scripting SuperApps Rebranding | 13 | 7 | 6 | Tidak Tercapai | Ewallet: 1. Ovo Positive 2. Dana Positive 3. ShopeePay Positive 4. LinkAja Positive 5. LinkAja Syariah Positive 6. Gopay Positive Berbagi: 1. Dompet Dhuafa Positive + Negative 2. Rumah Zakat Indonesia Positive + Negative 3. Kitabisa Positive + Negative 4. Jadiberkah Positive + Negative Profile: 1. Change Profile Pic 2. Delete Profile Pic 3. Change Email Positive + Negative
2023-03-17 | Scripting SuperApps Rebranding | 13 | 13 | 0 | Tercapai | Paket Data: 1. Telkomsel Positive + Negative 2. XL Positive + Negative 3. Tri Positive + Negative 4. Indosat Positive + Negative Download Mutasi N/A e statement: 1. Download Mutasi N/A e statement Current transaction: 1. View list recent transaction ( history) N/A transfer Positive + Negative 2. Update list recent transaction (history) N/A transfer Positive + Negative
2023-03-20 | Running dan Fixing Script | 5 | 5 | 0 | Tercapai | Pulsa dan Paket Data: 1. Pulsa XL Positive 2. Paket Data XL Positive Berbagi via Virtual Accout: 3. Dompet Dhuafa Positive 4. Rumah Zakat Indonesia Positive 5. Pengecekan Mutasi dan Jurnal melalui T24
2023-03-21 | Running dan Fixing Script | 9 | 9 | 0 | Tercapai | 1. Update List Recent Transaction Positive + Negative 2. View List Recent Transaction Positive + Negative 3. Social Media 4. Paket Data Telkomsel Positive 5. Pulsa Telkomsel Positive 6. ShopeePay Positive 7. Paket Data XL Positive 8. Rumah Zakat Indonesia Positive 9. Dompet Dhuafa Positive
2023-03-24 | Running dan Fixing Script | 6 | 6 | 0 | Tercapai | 1. Pulsa Indosat 2. Paket Data Indosat 3. Pulsa Tri 4. Paket Data Tri 5. Pulsa Smartfren 6. Download Mutasi E-Statement
2023-03-27 | Running | 6 | 6 | 0 | Tercapai | 1. Pulsa Indosat Negative 2. Pulsa Tri Positive + Negative 3. Pulsa Smartfren Positive + Negative 4. Download Mutasi E-Statement 5. Dompet Dhuafa Negative 6. Rumah Zakat Indonesia Negative
2023-03-30 | Running dan Fixing Script | 9 | 9 | 0 | Tercapai | 1. Universitas Ahmad Dahlan Negative 2. Universitas Andalas Negative 3. MPN DJBC Positive 4. MPN DJP Positive 5. MPN DJA Positive 6. Universitas Ahmad Dahlan Positive 7. Universitas Andalas Positive 8. Takaful Positive 9. CAR Tagihan Lainnya Positive
2023-04-04 | Running dan Fixing Script | 8 | 8 | 0 | Tercapai | 1. Akademik ahmad dahlan positive 2. Akademik ahmad dahlan negative 3. Akademik UIN STS Jambi Positive 4. Akademik UIN STS Jambi Negative 5. Tarik tunai tanpa kartu via atm bsi negative 6. Tarik tunai tanpa kartu via gerai indomaret negative 7. Lembaga Bayar ID positive 8. Paket data xl negative
2023-04-05 | Running dan Fixing Script | 8 | 8 | 0 | Tercapai | 1. MPN Negative 2. Pulsa Telkomsel Positive 3. Pulsa Tri Positive 4. Pulsa XL Positive 5. Paket Data Telkomsel Positive 6. Paket Data Tri Positive 7. Paket Data Indosat Positive 8. Gopay Positive
2023-04-10 | Running dan Fixing Script | 5 | 5 | 0 | Tercapai | 1. LinkAja Positive 2. Tarik Tunai Tanpa Kartu Indomaret Negative 3. Tarik Tunai Tanpa Kartu ATM BSI Negative 4. Paket Data XL Negative 5. Flow Favourite Transaction
2023-04-11 | Running SuperApp Rebrand | 12 | 12 | 0 | Tercapai | 1. Tarik Tunai Indomaret Positive 2. Tarik Tunai ATM BSI Positive 3. Link Aja Syariah Positive + Negative 4. LinkAja Negative 5. BPJS Ketenagakerjaan BPU Negative 6. Kitabisa Positive + Negative 7. List Recent Transaction Positive 8. Universitas Ahmad Dahlan Positive + Negative 9. Jadiberkah Positive Negative
2023-04-12 | Running SuperApp Rebrand | 4 | 4 | 0 | Tercapai | 1. Pelaporan Transaksi 2. Pelaporan Melalui Mutasi 3. Akademik Bayar ID Positive + Negative
2023-04-13 | Running SuperApp Rebrand | 13 | 13 | 0 | Tercapai | 1. Rumah Zakat Indonesia Positive + Negative 2. Pulsa Indosat Positive + Negative 3. Paket Data Telkomsel Positive + Negative 4. Paket Data Indosat Positive + Negative 5. Pulsa XL Positive + Negative 6. Pulsa Tri Positive
2023-04-14 | Running SuperApp Rebrand | 15 | 15 | 0 | Tercapai | 1. Pulsa Tri Negative 2. Paket Data Telkomsel Positive + Negative 3. Paket Data Tri Positive +Negative 4. Pulsa Smartfren Positive + Negative 5. Pulsa Telkomsel Positive + Negative 6. Dana Positive + Negative 7. Gopay Positive + Negative 8. Ovo Positive + Negative